## Project Plan
[11 empty] | 2016 | [17 empty] | 2017
Task or Deliverable |  |  |  | Planned Start Date | Actual Start Date | Planned Complete Date | Actual Complete Date | Status | % Complete | Owner(s) | 2016-08-29 | 2016-09-05 | 2016-09-12 | 2016-09-19 | 2016-09-26 | 2016-10-03 | 2016-10-10 | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02 | 2017-01-09 | 2017-01-16 | 2017-01-23 | 2017-01-30 | 2017-02-06 | 2017-02-13 | 2017-02-20 | 2017-02-27 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-04-17 | 2017-04-24 | 2017-05-01 | 2017-05-08
1.0 Initiate Project
1.1 Identify Stakeholders
1.2 Develop Project Charter
1.2.1 Define Scope
1.2.2 Define Requirements
1.2.3 Define Roles
1.2.4 Identify Controls
1.2.5 Identify Risks
1.2.6 Finalize Charter
1.2.6.1 Present Charter
1.2.6.2 Conduct Stakeholder Review
1.2.6.3 Make Changes as per review
1.2.6.4 Get Stakeholder Approval/Signoff
2.0 Plan Project
2.1 Develop High Level Project Plan
2.1.1 Develop Work Breakdown Structure
2.1.2 Develop Project Timeline
2.1.3 Define and Assign Project Responsibilities
2.2 Develop Project Control Plan
2.2.1 Develop Communication Plan
2.2.1.1 Select Team Collaboration Tool Selection
2.2.1.2 Select and Finalize Code Development and Sharing Tool
2.2.2 Develop Quality Control Plan
2.2.3 Develop Change Management Plan
2.3 Finalize Project Plan
2.3.1 Finalize Project Requirements
2.3.1.1 Develop Use Cases / User Stories
2.3.2 Finalize Technology Stack/Architecture
3.0 Complete Detailed Design
3.1 Design Application Structure
3.1.1 Define Application Flow
3.1.2 Design Wireframes
3.2 Design Database Schema and Architecture
3.2.1 Design Data Models
3.2.2 Design Database Schema
3.2.3 Detail out the MVC Components and Layers
3.4 Identify Content
3.4.1 Identify the Content to be used
3.4.2 Identify the images needed
3.4.3 Identify API's needed
3.4.4 Define front end standards ( e.g. CSS)
3.6 Conduct Stakeholder Review
4.0 Build and Test the Application
4.1 Create the Database
4.1.1 Load cdatabase values
4.1.2 Create entitity model relationships
4.2 Generate the Code Base
4.2.1 Write initial set of code
4.2.2 Create Github repository
4.2.3 Sync Code with Git
4.3 Test the Application
4.3.1 Test Application Flow
4.3.2 Test Application Content
4.3.3 Test Application Logic
4.3.4 Adjust Application
4.4 Create Application Screens
4.4.1 Create Screens
4.4.2 Design and Style using CSS
4.5 Test Application
4.5.1 Test Login screen
4.5.2 Test Screen FLows
4.5.3 Test Application Logic
4.5.4 Change Flows as needed
4.5.5 Conduct User Acceptance and Stakeholder Review
5.0 Deploy Application
5.1 Prep Code for Move to Production
5.2 Move to Production
5.3 Transfer Ownership to Client
5.3.1 Train Client
5.3.2 Transfer electronic content to client
6.0 Develop Project Communication Material
6.1 Develop User Manual
6.1.1 Develop User Manual
6.1.2 Conduct User Acceptance
6.2 Develop MIT Program Deliverables
6.2.1 Develop Term I Project Binder
6.2.2 Develop Term II Project Binder
6.2.3 Develop Final Client Project Presentation

## Project Team
Team
Mathew
Mike
Nhia
Brian
Glen